## Sheet1
Joshua's Development Plan
Task ID | Main Plan | Main Task | Start | End | Sub-tasks | Status
B2.1 | Develop interfaces between simulation models | T1. Complete the installation of the Switch interface | 2024-05-13 | 2024-05-14 | T1.1 - Go through the documentation on how to setup the Switch Interface | 100%
[5 empty] | T1.2 - Test out the Switch Interface using Google Collab, and ensure it runs correctly | 100%
[5 empty] | T1.3 - Install the Switch Interface onto my machine, ensuring the outputs match the Collab | 100%
[5 empty] | T1.4 - Install the Switch Interface on the Lab computer. | 100%
|  | T2. Install, run and review the mapping tool | 2024-05-16 | 2024-05-17 | T2.1- Install the mapping tool and follow the documentation | 100%
[5 empty] | T2.2 - Use the mapping tool, and understand the features | 100%
[5 empty] | T2.3 - Review the system's models such as functional, class diagrams, flow charts, etc | 100%
[5 empty] | T2.4 - Review the database architecture for the tool | 100%
|  | T3. Develop the PSM module of the User Interface | 2024-05-30 | 2024-06-15 | T3.1 - Develop a simple model of the home page and module, and present to the Professor before developing | 100%
[5 empty] | T3.2 - Implement the drag and drop/connection functionality into the user interface. | 100%
[5 empty] | T3.3 - Update all the node data with the meta-class data as provided in the project outline. | 100%
[5 empty] | T3.4 - Make an API endpoint for Omar to call when fetching data from the UI | 100%
[5 empty] | T3.5 - Revise Meta-class data with Omar's Ontology graph and github classes. | 90%
[5 empty] | T3.6 - Adjust Load and Inverter/Converter Components to have multiple component options | 100%
|  | T4. Develop the Map module of the User Interface | 2024-06-05 | 2024-06-07 | T4.1 - Integrate the mapping tool files into the React project, and install any outstanding or required libraries | 100%
[5 empty] | T4.2 - Create a component for the map to be loaded, and ensure functionality works | 100%
|  | T5. Develop the ESN module of the User Interface | 2024-06-11 | 2024-06-26 | T5.1 - Learn and use D3.js to visualize and represent the data. | 100%
[5 empty] | T5.2 - Create the network and handle data transfer/state management using React | 100%
[5 empty] | T5.3 - Add functionality such as dragging nodes, zooming, and list node data | 100%
[5 empty] | T5.4 - Add a detailed and non-detailed view of the network, where users can choose how to view. | 100%
[5 empty] | T5.5 - Include Value nodes as well, where it displays a parameters value | 100%
|  | T6. Develop Backend and update Energy Systems DB | 2024-06-27 | 2024-07-12 | T6.1 - Import Omar's Energy System Database into MySQL | 100%
[5 empty] | T6.2 - Develop a Flask backend to handle API requests from the User Interface | 100%
[5 empty] | T6.3 - Develop SQL queries to insert Energy Flow data into the Energy System Database | 100%
[5 empty] | T6.4 - Create additional API points to handle user login/registration | 100%
[5 empty] | T6.5 - Create endpoints to handle Collaboration uploads/downloads | 70%
[5 empty] | T6.6 - Create endpoints to handle Scenario UI requests | 50%
|  | T7. Develop the Home Page of the User Interface | 2024-05-30 | 2024-06-05 | T7.1 - Make a simple user interface, just for functionality | 100%
[5 empty] | T7.2 - Add logo and additional styling as per the Professor's request | 100%
[5 empty] | T7.3 - Update site information to include relevant details such as how to contact, and contributors to project | 100%
|  | T8. Develop the Collaboration module of the User Interface | 2024-07-08 | 2024-07-12 | T8.1 - Create CSV File download functionality | 70%
[5 empty] | T8.2 - Handle CSV File upload functionality | 70%
[5 empty] | T8.3 - Generate Output graph using Matplotlib | 100%
|  | T9. Develop the Scenarios module of the User Interface | 2024-07-01 | 2024-07-05 | T9.1 - Display all Scenarios based on energy sources selected in the PSM | 100%
[5 empty] | T9.2 - Generate all combinations of scenarios using Omar's python function | 100%
[5 empty] | T9.3 - Generate % use of each energy source for each combination | 30%
B2.4 | Collaborative Negotiation algorithm between views | T10. Research the negotiation algorithms | 2024-07-01 | TBA | T10.1 - Read research papers, and documentation regarding how LLMs utilize/implement these negotiations | 5%
[5 empty] | T10.2 - Research alternative implementations/approaches such as Game Theory or Reinforcement Learning. | 0%
[5 empty] | T10.3 - Share findings and relevant paper's with Omar to discuss | 0%